## Cover Page
Practical Software Engineering Series
TEST SUMMARY REPORT
Version : 0.1
Document Control information
Faculty | Faculty of Information Technology
Issue Date: | 2023-11-24
Author: | Trần Quang Khải
Confidential Class:
Document Revision History
Date | Version | Description | Revised by

## 0. Project Information
TEST SUMMARY REPORT
Project Information
Project Name
Description
Issue Date | 24/11/2023
Author | Trần Quang Khải
Reviewer Information | Name | Department | Position
Approver Information

## 1. Summary Report
TEST SUMMARY REPORT
OVERALL INFORMATION
Test Purpose | Functional Test
Number of testers | 4 members
OVERALL STATUS
Total Number of Test Cases | 143
Executed | Passed |  |  |  | 110
| Failed |  |  |  | 33
| Total Tests Executed (Passed + Failed) |  |  |  | 143
Not Executed
Blocked | 0
Number of Defects | High | 18 | Medium | 8 | Low |  | 0
| Total Defects (High + Medium + Low) |  |  |  | 26
Test Subject | Priority | Total Test Cases | Test Runs |  |  |  |  | Defects |  |  |  | Comments
|  |  | Status |  |  |  | Fail Rate | Total Defects | Line of code (LOC) | Defects fixed | Fixed Rate
|  |  | Passed | Failed | Not Executed | Blocked
View chart statistics of total teaching hours and converted hours by term and year & Export data into formats | High | 43 | 36 | 3 | 4 | 0 | 6.977% | 3 | 0 | 0 | 0%
View statistics in tabular form and details of total teaching hours and converted hours of individuals who are full-time teachers by Term and year | High | 75 | 50 | 7 | 18 | 0 | 9.333% | 7 | 0 | 0 | 0%
Update unit price & coefficient | High | 15 | 8 | 7 | 0 | 0 | 46.67% | 7 | 0 | 0 | 0%
New assignments and instructor updates | High | 13 | 5 | 7 | 1 | 0 | 53.85% | 2 | 0 | 0 | 0%
View rank list | High | 13 | 5 | 5 | 3 | 0 | 38.46% | 5 | 0 | 0 | 0%
Search rank list | High | 12 | 6 | 4 | 2 | 0 | 33.33% | 4 | 0 | 0 | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
Note on B18: Author: Liệt kê các chức năng hoặc chủ đề cần thực thi kiểm thử

## 2. Defects Report
DEFECTS REPORT
No. | Test Subject | Defect ID | Title | Steps to Reproduce | Evidences | Expected Result | Actual Result | Priority | Severity | Status | Raised By | Raised Date | Tested on build version
2 | Cập nhật Đơn giá & hệ số | DF_TLDG_01 | Hệ thống hiển thị thông báo lỗi khi người dùng để trống các trường dữ liệu. | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao -> Đơn giá & Hệ số 2. Trên giao diện Quản lý đơn giá & hệ số -> chọn năm học -> chọn CTĐT tiêu chuẩn -> chọn cấp bậc -> để trống trường Đơn giá và chọn lưu. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Bạn chưa nhập đơn giá" | Hệ thống hiển thị thông báo "Bạn chưa nhập đơn giá." ngay bên dưới trường Học kỳ, và con trỏ chuột nằm ở trường Học kỳ để người dùng có thể nhập lại. | High | High | Old
3 |  | DF_TLDG_02 | Hệ thống hiển thị thông báo lỗi khi người dùng nhập kí tự khoảng trắng ở các trường dữ liệu. | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao -> Đơn giá & Hệ số 2. Trên giao diện Quản lý đơn giá & hệ số -> chọn năm học -> chọn CTĐT tiêu chuẩn -> chọn cấp bậc -> nhập kí tự khoảng trắng ở trường dữ liệu và chọn lưu. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Bạn chưa nhập đơn giá" | Hệ thống hiển thị thông báo "Bạn chưa nhập đơn giá." ngay bên dưới trường Học kỳ, và con trỏ chuột nằm ở trường Học kỳ để người dùng có thể nhập lại. | High | High | Old
4 |  | DF_TLDG_03 | Hệ thống hiển thị thông báo lỗi khi người dùng để trống các trường dữ liệu. | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao -> Đơn giá & Hệ số 2. Trên giao diện Quản lý đơn giá & hệ số -> chọn năm học -> chọn CTĐT Đặc biệt -> chọn cấp bậc -> để trống trường Đơn giá và chọn lưu. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Bạn chưa nhập đơn giá" | Hệ thống hiển thị thông báo "Bạn chưa nhập đơn giá." ngay bên dưới trường Học kỳ, và con trỏ chuột nằm ở trường Học kỳ để người dùng có thể nhập lại. | High | High | Old
5 |  | DF_TLDG_04 | Hệ thống hiển thị thông báo lỗi khi người dùng nhập kí tự khoảng trắng ở các trường dữ liệu. | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao -> Đơn giá & Hệ số 2. Trên giao diện Quản lý đơn giá & hệ số -> chọn năm học -> chọn CTĐT Đặc biệt -> chọn cấp bậc -> nhập kí tự khoảng trắng ở trường dữ liệu và chọn lưu. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Bạn chưa nhập đơn giá" | Hệ thống hiển thị thông báo "Bạn chưa nhập đơn giá." ngay bên dưới trường Học kỳ, và con trỏ chuột nằm ở trường Học kỳ để người dùng có thể nhập lại. | High | High | Old
6 |  | DF_TLDG_05 | Hệ thống hiển thị thông báo lỗi khi người dùng để trống các trường dữ liệu. | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao -> Đơn giá & Hệ số 2. Trên giao diện Quản lý đơn giá & hệ số -> chọn năm học -> chọn Người nước ngoài -> chọn cấp bậc -> để trống trường Đơn giá và chọn lưu. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Bạn chưa nhập đơn giá" | Hệ thống hiển thị thông báo "Bạn chưa nhập đơn giá." ngay bên dưới trường Học kỳ, và con trỏ chuột nằm ở trường Học kỳ để người dùng có thể nhập lại. | High | High | Old
7 |  | DF_TLDG_06 | Hệ thống hiển thị thông báo lỗi khi người dùng nhập kí tự khoảng trắng ở các trường dữ liệu. | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao -> Đơn giá & Hệ số 2. Trên giao diện Quản lý đơn giá & hệ số -> chọn năm học -> chọn Người nước ngoài -> chọn cấp bậc -> nhập kí tự khoảng trắng ở trường dữ liệu và chọn lưu. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Bạn chưa nhập đơn giá" | Hệ thống hiển thị thông báo "Bạn chưa nhập đơn giá." ngay bên dưới trường Học kỳ, và con trỏ chuột nằm ở trường Học kỳ để người dùng có thể nhập lại. | High | High | Old
9 | Search by semester | DF_TK_09 | The system reports an error when the user selects a semester without data | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select search semester with lecturer information data |  | After performing step 2, the system displays the list of lecturers data information | The system displays information about the list of lecturers | Medium | Low | Old
10 | Search by industry | DF_TK_10 | The system reports an error when the user selects an industry with no data | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select search semester with lecturer information data |  | After performing step 2, the system displays lecturer data information | The system displays information about the list of lecturers | Medium | Low | Old
11 | Search by school year | DF_TK_11 | The system reports an error when the user selects a school year without data | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select search semester with lecturer information data |  | After performing step 2, the system displays lecturer data information | The system displays information about the list of lecturers | Medium | Low | Old
12 | Search by GV Code | DF_TK_12 | The system reports an error when the user selects a GV code that does not exist | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select view details. 3. select search for GV code where data exists |  | After performing step 2, the system displays lecturer data information | The system displays information about the list of lecturers | Medium | Low | Old
13 | Search by Teacher Name | DF_TK_13 | The system reports an error when the user selects a teacher name that does not exist | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select view details. 3. select to search for teachers' names whose data exists |  | After performing step 2, the system displays lecturer data information | The system displays information about the list of lecturers | Medium | Low | Old
14 | Search by class number | DF_TK_14 | The system reports an error when the user selects a number of classes that do not exist | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select view details. 3. select search for layer number where data exists |  | After performing step 2, the system displays lecturer data information | The system displays information about the list of lecturers | Medium | Low | Old
15 | Search by class details | DF_TK_15 | The system reports an error when the user selects a class detail that does not exist | 1. Log in with your BCN Khoa account and select statistics -> converted hours. 2. On the converted hours interface, select view details. 3. select detailed search where data exists |  | After performing step 2, the system displays lecturer data information | The system displays information about the list of lecturers | Medium | Low | Old
16 | Phân công mới và cập nhật giảng viên | DF_TK_01 | hệ thống hiển thị thông báo lỗi khi người dùng chọn trùng giáo viên đã phân công | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thời khóa biểu -> Phân công. 2. Trên giao diện Phân công giảng dạy chọn Học kì -> Chọn tiết cần phân công giảng viên -> chọn giảng viên đã đạt số lớp tối đa trong 1 tuần. |  | Sau khi thực hiện bước 2, hệ thống phải thông báo "Giảng viên này đã đạt số lớp tối đa trong 1 tuần." | Hệ thống hiển thị thông báo "Giảng viên này đã đạt số lớp tối đa trong 1 tuần !." và nút "OK" để đóng pop up. | High | Medium | Old
17 | Xem thống kê số giờ quy đổi dạng bảng biểu | DF_VTH_01 | Hệ thống không thể hiển thị dữ liệu số giờ quy đổi mà người dùng muốn xem vì hệ thống chưa thêm học kỳ/năm đó | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thống kê-> Chọn Số giờ quy đổi. 2. Trên giao diện Số giờ quy đổi chọn Học kì. |  | Sau khi thực hiện bước 2, hệ thống sẽ liệt kê các học kỳ mà đang tồn tại nhưng không có học kỳ mà người dùng muốn xem |  | Medium | Medium | Old
18 | Xem thống kê số giờ quy đổi dạng bảng biểu | DF_VTH_02 | Hệ thống không hiển thị dữ liệu ở học kỳ người dùng chọn vì không có dữ liệu ở chức năng Đơn giá & hệ số | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Thù lao-> Chọn Đơn giá & hệ số->Chọn Hệ số. 2. Trên giao diện Hệ số->Chọn học kỳ ->Kiểm tra dữ liệu->Không có dữ liệu được nhập vào hệ số ở học kỳ đó. 3. Chọn Thống kê -> Chọn Số giờ quy đổi->Chọn bảng biểu->Chọn học kỳ->Kiểm tra dữ liệu->Hệ thống thông báo không có dữ liệu ở học kỳ này |  | Sau khi thực hiện bước 3, hệ thống sẽ thông báo đến người dùng là không có dữ liệu để thống kê số giờ quy đổi | Hệ thống hiển thị thông báo "Chưa có dữ liệu" | High | High | Old
19 | Xem thống kê số giờ quy đổi dạng bảng biểu | DF_VTH_03 | Hệ thống không hiển thị dữ liệu ở học kỳ người dùng chọn vì không có dữ liệu ở Phân công & Thời khóa biểu | 1.Đăng nhập vào bằng tài khoản của BCN Khoa và chọn Phân công/ Thời khóa biểu->Kiểm tra dữ liệu->Không có dữ liệu. 2. Ở giao diện chức năng Thống kê->Chọn Số giờ quy đổi-> Chọn học kỳ->Chọn bảng biểu. |  | Sau khi thực hiện bước 2, hệ thống sẽ không có đủ dữ liệu để thống kê thành bảng biểu | Hệ thống hiển thị thông báo "Chưa có dữ liệu" | High | High | Old
20 | View rank list | DF_VRL_01 | Confirm the system does not display when the user has not entered a rank | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level. |  | after performing step 2. The system display the message "You have not entered a rank". | The system display the message "You have not entered a rank" | High | High | Old
21 |  | DF_VRL_02 | confirm that the system does not display when the user leaves a rank blank | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level. |  | after performing step 2. The system display the message "You have not entered a rank". | The system display the message "You have not entered a rank" | High | High | Old
22 |  | DF_VRL_03 | confirm that the system reports an error when the user assigns the wrong level | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level. |  | after performing step 2. The system display the message "You assigned the wrong rank". | The system display the message "You assigned the wrong rank". | High | High | Old
23 |  | DF_VRL_04 | confirm that the system displays missing information when the user has not fully entered the required information fields | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level. |  | after performing step 2. The level display system does not have complete information. | The level display system does not have complete information. | High | High | Old
24 |  | DF_VRL_05 | confirm this hierarchy display system does not exist | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level. |  | after performing step 2. The system does not display the 4th level without input data. | The system does not display the 4th level without input data | High | High | Old
25 | Search rank list | DF_SRL01 | Confirm that the system displays a successful message after the user enters the required information fierlds completely and in the correct form. | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level->Select search. |  | after performing step 2. The system closes the search form and displays the entered a rank. | The system closes the search form and displays the entered a rank. | High | High | Old
26 |  | DF_SRL02 | System confirmation is not displayed when the user leaves the rank blank. | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level->Select search. |  | after performing step 2. The system does not display success when the user has not entered a rank. | The system does not display success when the user has not entered a rank. | High | High | Old
27 |  | DF_SRL03 | Confirm the system does not display when the user enters the default information fields incorrectly | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level->Select search. |  | after performing step 2. The system does not display success when the user has not entered a rank. | The system does not display success when the user has not entered a rank. | High | High | Old
28 |  | DF_SRL04 | Confirm the system does not display when the user enters the default information fields incorrectly. | 1. Log in with your BCN Faculty account and select Remuneration/academic title, degree->check data. 2. In the Remuneration function interface->Select academic title, degree->Select level->Select search. |  | after performing step 2. The system does not display success when the user has not entered a rank. | The system does not display success when the user has not entered a rank. | High | High | Old
Note on C4: Author: Liệt kê các chức năng hoặc chủ đề cần thực thi kiểm thử
Note on F4: Author: Mô tả các bước thực hiện dẫn đến lỗi xuất hiện.
Note on G4: Author: Hình ảnh minh chứng cho lỗi tìm thấy
Note on I4: Author: Kết quả mong đợi trả về từ phần mềm cho bước đã mô tả ở cột Step to Reproduce
Note on J4: Author: Kết quả thực tế quan sát được từ phần mềm tại bước thực hiện đã mô tả ở cột Step to Reproduce
Note on K4: Author: Thứ tự ưu tiên sửa lỗi
Note on L4: Author: Mức độ ảnh hưởng của lỗi đối với phần mềm
Note on N4: Author: Họ tên của người đã tìm ra lỗi
Note on O4: Author: Ngày phát hiện ra lỗi
Note on P4: Author: Phiên bản của phần mềm dùng để chạy kiểm thử

## Data Range
Overall Progress | Test Run Status
On time | Passed | 0 | Test Subject | High | Medium | Low
Delayed | Failed | 0 | Login | 0 | 2 | 3
Stopped | Not Executed | 0 | Add User | 1 | 2 | 2
| Blocked | 0 | Update User | 0 | 3 | 1
Priority |  |  | Delete User | 1 | 1 | 0
High |  |  | Add Order | 0 | 3 | 1
Medium |  |  | Update Order | 0 | 0 | 2
Low |  |  | Delete Order | 0 | 1 | 2
|  |  | Add Shopping Cart | 0 | 2 | 1
Severity |  |  | Update Shopping Cart | 0 | 1 | 1
Critical |  |  | Create Order | 1 | 3 | 2
High
Medium
Low