## Cover Page
Practical Software Engineering Series
TEST SUMMARY REPORT
Version : 0.1
Document Control information
Faculty | Faculty of Information Technology
Issue Date:
Author:
Confidential Class:
Document Revision History
Date | Version | Description | Revised by

## 0. Project Information
TEST SUMMARY REPORT
Project Information
Project Name
Description
Issue Date
Author
Reviewer Information | Name | Department | Position
Approver Information

## 1. Summary Report
TEST SUMMARY REPORT
OVERALL INFORMATION
Test Purpose | Integration Test
Number of testers | 4
OVERALL STATUS
Total Number of Test Cases | 67
Executed | Passed |  |  |  | 67
| Failed |  |  |  | 0
| Total Tests Executed (Passed + Failed) |  |  |  | 67
Not Executed | 0
Blocked | 0
Number of Defects | High | 1 | Medium |  | Low
| Total Defects (Critical + High + Medium) |  |  |  | 1
Test Subject | Priority | Total Test Cases | Test Runs |  |  |  |  | Defects |  |  |  | Comments
|  |  | Status |  |  |  | Fail Rate | Total Defects | Line of code (LOC) | Defects fixed | Fixed Rate
|  |  | Passed | Failed | Not Executed | Blocked
Faculty board - Faculty board | High | 31 | 31 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Faculty board - Lecturer | High | 12 | 12 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Lecturer - Department | High | 9 | 9 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0%
Faculty board - Department | High | 16 | 15 | 1 | 0 | 0 | 6.25% | 1 | 0 | 0 | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
|  | 0 |  |  |  |  | 0% |  |  |  | 0%
Note on B18: Author: Liệt kê các chức năng hoặc chủ đề cần thực thi kiểm thử

## 2. Defects Report
DEFECTS REPORT
No. | Test Subject | Defect ID | Title | Steps to Reproduce | Evidences | Expected Result | Actual Result | Priority | Severity | Status | Raised By | Raised Date | Tested on build version
| search for lecturers | DF_TK_01 | The system will display the message "No results found" when the user's lecturer information has not been imported. | 1. Log in with your BCN Faculty account and select schedule -> assignment 2. On the assignment interface, enter the name of the lecturer who already has data from the lecturer filter. |  | After performing step 2, the system displays the lecturer's data information that has just been searched | The system displays data information of that lecturer. | High | High | New
Note on C4: Author: Liệt kê các chức năng hoặc chủ đề cần thực thi kiểm thử
Note on F4: Author: Mô tả các bước thực hiện dẫn đến lỗi xuất hiện.
Note on G4: Author: Hình ảnh minh chứng cho lỗi tìm thấy
Note on I4: Author: Kết quả mong đợi trả về từ phần mềm cho bước đã mô tả ở cột Step to Reproduce
Note on J4: Author: Kết quả thực tế quan sát được từ phần mềm tại bước thực hiện đã mô tả ở cột Step to Reproduce
Note on K4: Author: Thứ tự ưu tiên sửa lỗi
Note on L4: Author: Mức độ ảnh hưởng của lỗi đối với phần mềm
Note on N4: Author: Họ tên của người đã tìm ra lỗi
Note on O4: Author: Ngày phát hiện ra lỗi
Note on P4: Author: Phiên bản của phần mềm dùng để chạy kiểm thử

## Data Range
Overall Progress | Test Run Status
On time | Passed | 0 | Test Subject | Critical | High | Medium
Delayed | Failed | 0 | Login | 0 | 2 | 3
Stopped | Not Executed | 0 | Add Product | 1 | 2 | 2
| Blocked | 0 | Update Product | 0 | 3 | 1
Priority |  |  | Delete Product | 1 | 1 | 0
High |  |  | Add Order | 0 | 3 | 1
Medium |  |  | Update Order | 0 | 0 | 2
Low |  |  | Delete Order | 0 | 1 | 2
|  |  | Add Shopping Cart | 0 | 2 | 1
Severity |  |  | Update Shopping Cart | 0 | 1 | 1
Critical |  |  | Create Order | 1 | 3 | 2
High
Medium
Low